Tiffield Parish Council – Briefing Update

Subject: Roll-Out of Tiffield Village App (Heylo)
Date: 13/4/2026
Author: Cllr Nichols

Purpose of Update

To provide an overview of the planned roll-out of the Tiffield Village App (Heylo) and outline the initial implementation approach, engagement activities, and next steps ahead of the proposed May launch.

Background

The Parish Council has agreed to introduce the Heylo app as a new digital communication tool for residents. Following discussion, it has been decided that the app will be initially deployed in a controlled Phase 1 format, focusing solely on its use as an emergency alert system.

Phase 1 Scope

The app will be used specifically for push notifications relating to urgent and time-sensitive information, including:

- Weather alerts

- Flooding updates

- Road closures and traffic issues

- Crime and safety alerts

All other functionality within the app will be restricted during Phase 1 to ensure clarity of purpose, minimise misuse, and maintain effective governance.

Governance & Administration

To support a structured and secure rollout:

- Cllr Holdridge will draft a formal process for Parish Council use of the app

- All existing administrators will be removed, with access restricted to a designated working group

- App functionality will be locked down in line with Phase 1 objectives

This approach will ensure consistent messaging, accountability, and appropriate control over communications.

Community Engagement & Roll-Out Plan

A programme of communications and support will be delivered to encourage uptake across the village:

- Printed leaflets providing step-by-step guidance on downloading and using the app

- Facebook communications, including “how-to” posts and reminders

- Drop-in support sessions (dates to be confirmed) to assist residents with installation

- Offers to present at local groups, including:

  - FOTS (Friends of Tiffield School)

  - Tiffield Photography Group

  - History of Tiffield Society

In recognition of varying levels of digital confidence, residents will be encouraged to nominate a trusted family member or friend to download the app and receive alerts on their behalf, ensuring wider community coverage.

Next Steps

- Finalise governance and operating procedures (Cllr Holdridge)

- Develop and distribute communication materials

- Confirm dates for drop-in sessions and community presentations

- Prepare app for restricted Phase 1 use

Launch Timeline

The Parish Council is targeting a village-wide launch in May, subject to completion of the above actions.

Summary

The phased introduction of the Heylo app as an emergency alert system represents a practical and controlled approach to improving communication with residents. The planned engagement activities and governance measures will support a successful launch and lay the groundwork for potential future expansion of functionality.